## Slide 1
Project Update for Robo4Me
12th November 2021

## Slide 2
Project Plan - Milestones for 3 months
October 2021
Understanding competitive landscape and contribution to business plan
Figure out the capability level of allocated interns and assigning tasks
Create Approach Note for Trading Strategies – overall architecture
November 2021
Formulating Trading Strategies with inputs provided by Robo4me
Develop Trading Strategy models
Work on Back testing with the help from interns
December 2021
Evaluation of Trading Strategy on the basis of back testing results
Provide solutions for portfolio construction and management

## Slide 3
Project Status
October 2021
Understanding competitive landscape and contribution to business plan
Done. Focused on Betterment and Welathfront.
Figure out the capability level of allocated interns and assigning tasks
Worked with Divyant and Askshay. With Lokesh, going forward.
Create Approach Note for Trading Strategies – overall architecture
Done. Presented on 11th Nov.
November 2021
Formulating Trading Strategies with inputs provided by Robo4me
Ongoing
Develop Trading Strategy models
Ongoing
Work on Back testing with the help from interns
To begin

## Slide 4
Additional Involvement
Team members
Guidance and discussion for Ankit, Akshay and Divyant
Work on user profiles
Questionnaire development for Walmart’s Robo User
Research on specific user profiles and risk assessment frameworks
Miscellaneous
Research and understanding on GenZ users
Investment product discussions for HNIs

## Slide 5
Effort Involved from EMAlpha
October
>100 hours
November
~70 hours (till 12th November)

## Slide 6
Major challenges
Scope of work for EMAlpha
Last month was a learning experience
Hopefully, we collectively will do better now on
EMAlpha will keep the involvement to direct portfolio related discussions
Team structure
Lack of clarity on project ownership
Decision making on portfolio construction
Effort involved
So far, it is around 2x of how we estimated this

## Slide 7
Next Steps
November 2021
Freezing Trading Strategy models
Work on Back testing with the help from interns
December 2021
Evaluation of Trading Strategy on the basis of back testing results
Final solution for portfolio construction and management

## Slide 8
Thanks